## Lab3-Tasks
ID | Owner | % Completed | Task description | Comment
1 | Team | 0% | Write pseudocode for function static ??? get_char(???);
2 | Team | 0% | Write pseudocode for function static ??? skip_comment(???);
3 | Team | 0% | Write pseudocode for function static ??? skip_blanks(???);
4 | Team | 0% | Write pseudocode for function static ??? get_word(???);
5 | Team | 0% | Write pseudocode for function static ??? get_number(???);
6 | Team | 0% | Write pseudocode for function static ??? get_string(???);
7 | Team | 0% | Write pseudocode for function static ??? get_special(???);
8 | Team | 0% | Write pseudocode for function static ??? downshift_word(???);
9 | Team | 0% | Write pseudocode for function static BOOLEAN is_reserved_word(???);
10 | Vivian | 65% | Implement function static ??? get_char(???);
11 | Team | 20% | Implement function static ??? skip_comment(???);
12 | Vivian | 70% | Implement function static ??? skip_blanks(???);
13 | Vivian | 80% | Implement function static ??? get_word(???);
14 | Team | 0% | Implement function static ??? get_number(???);
15 | Team | 10% | Implement function static ??? get_string(???);
16 | Team | 0% | Implement function static ??? get_special(???);
17 | Vivian | 75% | Implement function static ??? downshift_word(???);
18 | Vivian | 80% | Implement function static BOOLEAN is_reserved_word(???);
19 | Team | 0% | Write functional test code for function static ??? get_char(???);
20 | Team | 0% | Write functional test code for function static ??? skip_comment(???);
21 | Team | 0% | Write functional test code for function static ??? skip_blanks(???);
22 | Team | 0% | Write functional test code for function static ??? get_word(???);
23 | Team | 0% | Write functional test code for function static ??? get_number(???);
24 | Team | 0% | Write functional test code for function static ??? get_string(???);
25 | Team | 0% | Write functional test code for function static ??? get_special(???);
26 | Team | 0% | Write functional test code for function static ??? downshift_word(???);
27 | Team | 0% | Write functional test code for function static BOOLEAN is_reserved_word(???);
28 | Vivian | 10% | Write system test code for function main
29 | Team | 100% | Create empty template doc for Pseudocode-Design | Pseudocode-Design.docx
30 | Team | 100% | Create empty template doc for Functional-Test-Table | Functional-Test-Table.docx
31 | Team | 100% | Create empty template doc for System-Test-Table | Functional-Test-Table.docx
32 | Team | 100% | Create doc for Team-Contribution-Assessment | Team-Contribution-Assessment.docx
33 | Team | 100% | Create empty template doc for Solution-Document | Solution-Document.docx
34 | Team | 100% | Create empty template doc for Change-History | Change-History.docx
35 | Team | 100% | Create empty template for Makefile | Makefile

## Lab3-CheckList
Item to be hand in | Description | Status
Pseudocode-Design.docx | pseudocode for each function | Created but empty
Functional-Test-Table.docx | a test table of all the tests you want to run for the program (functional tests) | Created but empty
System-Test-Table.docx | a test table for the main function (system tests) | Created but empty
C source files | test code for each item in the functional test system test table | not started
Team-Contribution-Assessment.docx | Team contribution table | Created but empty
Solution-Document.docx | Design document With URL | Created but empty
C source files | Actual source code | not started
Change-History.docx | Github change history | Created but empty
Makefile | Make file | not started

## TokenCode
Token Code | Token Type
AND | INTEGER_LIT
ARRAY | REAL_LIT
BEGIN | STRING_LIT
CASE
COLON
COLONEQUAL
COMMA
CONST
DIV
DO
DOTDOT
DOWNTO
ELSE
END
END_OF_FILE
EQUAL
ERROR
FFILE
FOR
FUNCTION
GE
GOTO
GT
IDENTIFIER
IF
IN
LABEL
LBRACKET
LE
LPAREN
LT
MINUS
MOD
NE
NIL
NO_TOKEN
NOT
NUMBER
OF
OR
PACKED
PERIOD
PLUS
PROCEDURE
PROGRAM
RBRACKET
RECORD
REPEAT
RPAREN
SEMICOLON
SET
SLASH
STAR
STRING
THEN
TO
TYPE
UNTIL
UPARROW
VAR
WHILE
WITH